## Executive_EVM_Dashboard
HELIOS 100MW SOLAR PV + 33/220kV GSS — EXECUTIVE EVM & WORK PACKAGE CONTROL DASHBOARD
Contract: FIDIC Yellow Book 1999 ¦ Location: Bukhara, Uzbekistan ¦ Simulation Clock: Day 001 (2026-10-06 — LNTP Start Position) ¦ Source: state/baseline.json
CONTRACT PRICE (BAC) |  | SIMULATION CLOCK |  | PLANNED VALUE (BCWS) |  | EARNED VALUE (BCWP) |  | ACTUAL COST (ACWP) |  | SCHEDULE INDEX (SPI) |  | COST INDEX (CPI)
85000000 |  | Day 001 (LNTP) |  | 53125 |  | 52878.75 |  | 55925 |  | 0.99536 |  | 0.94553
Fixed Lump Sum (FIDIC Yellow Book) |  | Date: 2026-10-06 (M1 / W1 / D1) |  | Day 001 Baseline S-Curve Target |  | QC-Accepted Progress Earned |  | Certified Cost Incurred |  | Target >= 0.95 (Green) |  | Target >= 0.95 (Green)
WP ID | Work Package Description | Discipline | Owner Agent | Unit | Budget BAC ($) | Scope Qty | Day 1 BCWS ($) | Installed Qty | QC Accepted Qty | Earned BCWP ($) [Auto] | Actual ACWP ($) | Cost Var CV ($) [Auto] | Status
WP-ENG-CIV | Civil, Geotechnical & Site Drainage Design | Engineering | TERRA | % | 1050000 | 100 | 8925 | 0.85 | 0.8075 | 8478.75 | 9100 | -621.25 | ACTIVE
WP-ENG-ELE | Electrical & Grid Interconnection Design | Engineering | AMPERE | % | 1600000 | 100 | 12000 | 0.75 | 0.7125 | 11400 | 12300 | -900 | ACTIVE
WP-ENG-MEC | Mechanical & Tracker Structural Design | Engineering | SOLARIS | % | 800000 | 100 | 5600 | 0.7 | 0.665 | 5320 | 5750 | -430 | ACTIVE
WP-ENG-SUB | 220kV Substation & Protection Design | Engineering | VOLTA | % | 800000 | 100 | 6400 | 0.8 | 0.76 | 6080 | 6550 | -470 | ACTIVE
WP-PROC-PIL | Foundation Ramming Piles Supply (15,400 pcs) | Procurement | DEPOT | piles | 1540000 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | RFQ PREP
WP-PROC-TRK | Single-Axis Trackers & Steel Structures | Procurement | FORGE | tables | 8500000 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | RFQ PREP
WP-PROC-MOD | 100MW Bifacial Solar PV Modules (580W TOPCon) | Procurement | FORGE | modules | 22000000 | 172800 | 0 | 0 | 0 | 0 | 0 | 0 | RFQ PREP
WP-PROC-INV | Central Inverters & MV Skids (25 x 4.0MVA) | Procurement | FORGE | skids | 5500000 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | SPEC ALIGN
WP-PROC-TRA | 220kV/33kV 100MVA Main Power Transformer | Procurement | FORGE | units | 1800000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CRITICAL RFQ
WP-PROC-GIS | 220kV GIS Switchgear & Primary Equipment | Procurement | FORGE | sets | 2200000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CRITICAL RFQ
WP-PROC-CAB-DC | 1.5kV DC Solar Cables & String Harnesses | Procurement | DEPOT | meters | 3260000 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | MTO PREP
WP-PROC-CAB-MV | 33kV MV Underground Cables & Joint Kits | Procurement | DEPOT | meters | 1200000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | MTO PREP
WP-PROC-BOP | Substation & Plant Balance of Plant Materials | Procurement | DEPOT | % | 5000000 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | MTO PREP
WP-CON-MOB | Site Mobilization, Security & Temp Facilities | Construction | BASTION | % | 1500000 | 100 | 20200 | 1.51 | 1.44 | 21600 | 22225 | -625 | ACTIVE
WP-CON-CIV-GRD | Site Clearing, Bulk Earthworks & Access Roads | Construction | BASTION | % | 2500000 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M2
WP-CON-CIV-PIL | PV Field Pile Ramming (Blocks 1-6) | Construction | BASTION | piles | 2200000 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M4
WP-CON-MEC-TRK | Single-Axis Tracker Assembly & Erection | Construction | STRATUM | tables | 4500000 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M5
WP-CON-MEC-MOD | PV Module Mounting & Fastening | Construction | STRATUM | modules | 4800000 | 172800 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M6
WP-CON-ELE-DC | DC Cable Trenching & String Cabling | Construction | CONDUIT | meters | 3000000 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M6
WP-CON-ELE-MV | 33kV MV Trenching, Laying & Termination | Construction | ARCLINE | meters | 2000000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M7
WP-CON-CIV-FND | Inverter & Substation Concrete Foundations | Construction | FORTRESS | m3 | 1800000 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M3
WP-CON-SUB-ERE | 220kV GSS Substation Erection & HV Line | Construction | SWITCHMAN | % | 3200000 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M10
WP-TNC-ALL | Cold/Hot Commissioning, 220kV Sync & PR Test | T&C | IGNITE | % | 4250000 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | PLANNED M15
TOTAL | Consolidated HELIOS 100MW EPC Portfolio | All | ATLAS | USD | 85000000 |  | 53125 |  |  | 52878.75 | 55925 | -3046.25 | ON TRACK
Discipline | Contract Weight | Baseline Budget ($) | Day 1 Earned BCWP ($) | Day 1 Actual ACWP ($)
Engineering | 5% | 4250000 | 31278.75 | 33700
Procurement | 60% | 51000000 | 0 | 0
Construction | 30% | 25500000 | 21600 | 22225
T&C | 5% | 4250000 | 0 | 0

## Baseline_S_Curve_18M
HELIOS EPC — 18-MONTH (504-DAY) REV 0 BASELINE S-CURVE & MILESTONE SCHEDULE
28-Day Simulation Months ¦ Total Contract Price (BAC): USD 85,000,000 ¦ Critical Path: 220kV GSS & 100MVA MPT (0 Days Float)
Sim Month | Sim Day End | Calendar Date | Key Milestone Gate | Monthly Planned Spend ($) | Cumulative BCWS ($) [Auto] | Cumulative Plan % [Auto] | Primary Active Workfronts | Critical Path Status
M01 | 28 | 2026-11-02 | HEL.00 LNTP & MPT PO Award (Day 12) | 1487500 | 1487500 | 1.75% | Basic Design, Geotech, Site Camp & Fencing | CRITICAL (MPT PO)
M02 | 56 | 2026-11-30 | HEL.20 Site Mobilization Complete | 2125000 | 3612500 | 4.25% | Detailed Design, Mass Grading & GIS PO | CRITICAL (GSS Eng)
M03 | 84 | 2026-12-28 | HEL.30 Engineering Freeze & Module PO | 3400000 | 7012500 | 8.25% | IFC Release, Inverter Pads & Module/Tracker POs | CRITICAL (MPT Mfg)
M04 | 112 | 2027-01-25 | HEL.20.CIV First Pile Driven | 4675000 | 11687500 | 13.75% | PV Field Piling Campaign (Blocks 1-5) & GSS Civil | CRITICAL (MPT Mfg)
M05 | 140 | 2027-02-22 | Tracker Steel Delivery & Piling Peak | 5950000 | 17637500 | 20.75% | Piling Blocks 1-6, Tracker Bearings & Plinths | CRITICAL (MPT Mfg)
M06 | 168 | 2027-03-22 | HEL.SCM.MOD First Module Delivered | 8500000 | 26137500 | 30.75% | First 580W TOPCon Modules On-Site & Tracker Erection | NEAR-CRITICAL (Mods)
M07 | 196 | 2027-04-19 | PCS Skids Delivered & MV Trenching | 9350000 | 35487500 | 41.75% | Module Mounting, 33kV MV Cable Laying & PCS Setting | CRITICAL (MPT FAT)
M08 | 224 | 2027-05-17 | 50% PV Field Module Mounting | 8925000 | 44412500 | 52.25% | Peak Module & DC Harness Installation | CRITICAL (MPT Ship)
M09 | 252 | 2027-06-14 | 220kV MPT Khorgos Border Transit | 7650000 | 52062500 | 61.25% | Khorgos Customs Clearance & Heavy-Haul to Bukhara | CRITICAL (Khorgos)
M10 | 280 | 2027-07-12 | 220kV MPT & GIS Site Arrival | 6800000 | 58862500 | 69.25% | MPT Plinth Skidding, GIS Clean-Room Erection | CRITICAL (GSS E&M)
M11 | 308 | 2027-08-09 | 75% PV Array & DC/MV Cabling | 5950000 | 64812500 | 76.25% | Substation Busbar, Protection Panels & SCADA Fiber | CRITICAL (GSS E&M)
M12 | 336 | 2027-09-06 | Civil Completion & All Modules On-Site | 5100000 | 69912500 | 82.25% | Final Module Strings, Transformer Oil Filling & SFRA | CRITICAL (MPT Test)
M13 | 364 | 2027-10-04 | Pre-Commissioning & Cold Testing Start | 4250000 | 74162500 | 87.25% | IEC 62446 String Voc/Isc/IR & BESS Reserve Grading | CRITICAL (Relay Test)
M14 | 392 | 2027-11-01 | 220kV Protection & Relay Injection | 3400000 | 77562500 | 91.25% | Secondary Injection, UzbekEnergo Settings Approval | CRITICAL (Grid Code)
M15 | 420 | 2027-11-29 | HEL.15 Mechanical Completion (100%) | 2975000 | 80537500 | 94.75% | MC Walkdowns, IV Curve / EL Audits & Snag Closure | CRITICAL (MC Gate)
M16 | 448 | 2027-12-27 | HEL.TNC.ENG First Back-Feed Energisation | 2125000 | 82662500 | 97.25% | Uzenergoinspeksiya Act & 220kV GSS Back-Feed | CRITICAL (Grid Sync)
M17 | 476 | 2028-01-24 | Hot Commissioning & 7-Day PR Test | 1487500 | 84150000 | 99% | Inverter Sync, PPC PFR Test & IEC 61724 PR >= 80% | CRITICAL (PR Test)
M18 | 504 | 2028-02-21 | HEL.10 Grid Sync / COD / PAC Handover | 850000 | 85000000 | 100% | Provisional Acceptance Certificate (PAC) & Commercial Ops | COD MILESTONE
TOTAL | 504 | 18 Months | Full Lifecycle Baseline | 85000000 | 85000000 | 100% | 100MW Solar PV + 33/220kV GSS Complete | 100% BAC

## Master_Document_Register
HELIOS EPC — MASTER DOCUMENT & DRAWING REGISTER (MDR) — START POSITION (DAY 001)
Custodians: HERALD (Document Controller, PM-03) & ARCHON (Design Manager, EN-01) ¦ FIDIC Sub-Clause 5.2 Review Period: 14 Calendar Days
Doc Number | Document / Drawing Title | Discipline | Owner Agent | Rev | Transmittal Ref | Sim Day Submitted | 14d Review Due Day [Auto] | Primary Reviewers | Review Status Code | IFC Released? | Linked Work Package
HEL-PM-PLN-0001 | Project Execution Plan (PEP) & PMO Governance Charter | PMO | ATLAS | Rev 0 | TRN-HEL-0001 | 1 | 15 | PATRON, AUDITOR | Code 1: Approved | YES | WP-CON-MOB
HEL-PL-SCH-0001 | Master EPC Baseline Schedule (L1-L3 P6 CPM) & S-Curve | PLN | KRONOS | Rev 0 | TRN-HEL-0002 | 1 | 15 | PATRON, AUDITOR | Code 1: Approved | YES | ALL WPs
HEL-HS-PLN-0001 | Construction HSE Plan & SanPiN Extreme Weather Protocol | EHS | AEGIS | Rev 0 | TRN-HEL-0003 | 1 | 15 | PATRON, AUDITOR, INSPECTOR | Code 1: Approved | YES | WP-CON-MOB
HEL-QA-PLN-0001 | Project Quality Plan (PQP) & Master ITP Schedule | QAQ | SENTINEL | Rev 0 | TRN-HEL-0004 | 1 | 15 | PATRON, AUDITOR | Code 1: Approved | YES | WP-CON-MOB
HEL-CV-GEO-0001 | Site-Wide Geotechnical Investigation Report (Blocks 1-6) | ENG-CIV | MERIDIAN | Rev A | TRN-HEL-0005 | 1 | 15 | TERRA, AUDITOR | Pending Review | NO | WP-ENG-CIV
HEL-ST-CAL-0010 | Driven Steel Pile Foundation Structural Calculations | ENG-CIV | TERRA | Rev A | TRN-HEL-0006 | 1 | 15 | ARCHON, AUDITOR, INSPECTOR | Pending Review | NO | WP-CON-CIV-PIL
HEL-MC-LAY-0100 | 1P Single-Axis Tracker Array General Layout & Loads | ENG-MEC | SOLARIS | Rev A | TRN-HEL-0007 | 1 | 15 | TERRA, AUDITOR | Pending Review | NO | WP-CON-MEC-TRK
HEL-EL-SLD-0100 | 1500V DC Array & 33kV MV Collector System SLD | ENG-ELE | AMPERE | Rev A | TRN-HEL-0008 | 1 | 15 | VOLTA, AUDITOR | Pending Review | NO | WP-CON-ELE-DC
HEL-HV-SLD-0101 | 33/220kV Grid Substation (GSS) Master Single Line Diagram | ENG-SUB | VOLTA | Rev A | TRN-HEL-0009 | 1 | 15 | GRIDMASTER, AUDITOR | Pending Review | NO | WP-ENG-SUB
HEL-PR-PHL-0200 | 33/220kV GSS Protection, Control & Metering Philosophy | ENG-PRO | CIPHER | Rev A | TRN-HEL-0010 | 1 | 15 | GRIDMASTER, AUDITOR | Pending Review | NO | WP-ENG-SUB
HEL-SC-PLN-0001 | Master Procurement Plan, AVL & Two-Envelope Bidding SOP | SCM | CONVOY | Rev 0 | TRN-HEL-0011 | 1 | 15 | ATLAS, PATRON | Code 1: Approved | YES | WP-PROC-TRA
HEL-CM-ins-0001 | Performance Security (10%), APBG & CAR/Marine Insurance Dossier | COM | LEDGE | Rev 0 | TRN-HEL-0012 | 1 | 15 | COUNSEL, PATRON | Code 1: Approved | YES | ALL WPs

## Procurement_MIRN_Tracker
HELIOS EPC — MASTER PROCUREMENT, KHORGOS LOGISTICS & SITE STORES (MIRN) TRACKER
Owners: CONVOY (SCM Mgr), FORGE (Long-Lead), DEPOT (BOP), TRACER (Expediter), ROUTE (Customs), VAULT (Stores) ¦ Two-Envelope AVL Protocol
Package ID | Equipment / Material Scope | Buyer | OEM Vendor | Package Budget ($) | 15% Advance ($) [Auto] | 75% LC Ship ($) [Auto] | 10% Ret ($) [Auto] | PO Drop-Dead Day | Lead Time (Days) | ROSD Target Day [Auto] | Delivered Qty | Status
WP-PROC-TRA | 220kV/33kV 100MVA Main Power Transformer (ONAN/ONAF) | FORGE | POWERTRANS | 1800000 | 270000 | 1350000 | 180000 | 12 | 182 | 194 | 0 | CRITICAL RFQ (0d Float)
WP-PROC-GIS | 220kV SF6 Gas Insulated Switchgear (40kA/3s) | FORGE | POWERTRANS | 2200000 | 330000 | 1650000 | 220000 | 45 | 168 | 213 | 0 | CRITICAL RFQ
WP-PROC-MOD | 100MW Bifacial Solar PV Modules (172,800 pcs 580W TOPCon) | FORGE | LUMINOS | 22000000 | 3300000 | 16500000 | 2200000 | 75 | 90 | 165 | 0 | NEAR-CRITICAL RFQ
WP-PROC-TRK | 1P Single-Axis Trackers & Steel Structures (5,100 tables) | FORGE | AVL Shortlist | 8500000 | 1275000 | 6375000 | 850000 | 60 | 70 | 130 | 0 | MTO ALIGNMENT
WP-PROC-INV | Central Inverters & 33kV MV Skids (25 x 4.0MVA + PPC) | FORGE | INVERSA | 5500000 | 825000 | 4125000 | 550000 | 90 | 98 | 188 | 0 | SPEC ALIGNMENT
WP-PROC-PIL | Galvanized H-Piles for PV Foundations (15,400 piles) | DEPOT | AVL Shortlist | 1540000 | 231000 | 1155000 | 154000 | 40 | 60 | 100 | 0 | RFQ IN DRAFT
WP-PROC-CAB-DC | 1.5kV Solar DC String & Main Cables (1,300 km) | DEPOT | AVL Shortlist | 3260000 | 489000 | 2445000 | 326000 | 70 | 65 | 135 | 0 | MTO ALIGNMENT
WP-PROC-CAB-MV | 33kV XLPE Underground MV Cables & Cold-Shrink Kits (30 km) | DEPOT | AVL Shortlist | 1200000 | 180000 | 900000 | 120000 | 80 | 70 | 150 | 0 | MTO ALIGNMENT
WP-PROC-BOP | Substation & Plant Balance of Plant (RMUs, Earthing, Fiber) | DEPOT | AVL Shortlist | 5000000 | 750000 | 3750000 | 500000 | 90 | 84 | 174 | 0 | MTO ALIGNMENT
TOTAL | Total Procurement Portfolio (60% of Contract Price) | CONVOY | All OEMs | 51000000 | 7650000 | 38250000 | 5100000 |  |  |  | 0 | ACTIVE

## Quality_ITP_and_HSE_PTW
HELIOS EPC — QUALITY ITP HOLD POINTS, HSE PERMITS TO WORK (PTW) & UZBEKISTAN STATUTORY TRACKER
Custodians: SENTINEL (QA/QC Manager), AEGIS (EHS Manager) & PERMIT (Statutory Liaison) ¦ Start Position: Day 001 (2026-10-06)
Control / Permit ID | Category | WBS / Work Package | Activity / Inspection / Permit Scope | Governing Standard / Uzbekistan Norm | Internal Owner | External Witness / Authority | Gate Type | Day 001 Status
HEL-IR-CIV-001 | QA/QC ITP | WP-CON-MOB | Perimeter Fencing, Security Gates & Camp Readiness | Project Spec / HEL-QA-PLN-0001 | PLUMBLINE | AUDITOR (M) | W (Witness) | ACTIVE
HEL-IR-CIV-002 | QA/QC ITP | WP-CON-CIV-GRD | Mass Grading Sub-Grade Compaction & Internal Roads | NDG >= 95% MDD, CBR per KMK, +-50mm | PLUMBLINE | AUDITOR (W) | H (Hold Point) | SCHEDULED M2
HEL-IR-CIV-003 | QA/QC ITP | WP-CON-CIV-PIL | Pre-Construction Pile Static Load Tests (Compression/Uplift/Lateral) | ASTM D1143 / D3689 (>=1.5x) / D3966 (<=6mm), KMK 2.02.01-98 | PLUMBLINE | AUDITOR (H), INSPECTOR | H (Hold Point) | MANDATORY PRE-PILING
HEL-IR-CIV-004 | QA/QC ITP | WP-CON-CIV-PIL | Production Driven Pile Acceptance (E-W <= 20mm, Head <= 6mm) | HEL-ST-CAL-0010 / SOLARIS Spec | PLUMBLINE | AUDITOR (W) | H (Hold Point) | SCHEDULED M4
HEL-IR-MEC-001 | QA/QC ITP | WP-CON-MEC-TRK | 1P Tracker Bearing, Torque Tube & Slew Drive Bolt Torque Check | OEM Torque Spec + 100% Torque-Seal Marks | TORQUE | AUDITOR (W) | H (Hold Point) | SCHEDULED M5
HEL-IR-MEC-002 | QA/QC ITP | WP-CON-MEC-MOD | 580W Bifacial Module Clamping Zone & Torque (14-20 Nm) | LUMINOS Manual / IEC 62446-1 | TORQUE | AUDITOR (W) | H (Hold Point) | SCHEDULED M6
HEL-IR-ELE-001 | QA/QC ITP | WP-CON-ELE-DC | DC String Polarity, Voc, Isc, Megger IR & IV Curve (FF >= 78%) | IEC 62446-1 / IEC 62930 | OHMMETER | AUDITOR (W) | H (Hold Point) | SCHEDULED M13
HEL-IR-ELE-002 | QA/QC ITP | WP-CON-ELE-MV | 33kV MV Cable Cold-Shrink Jointing (Tent) & 0.1Hz VLF Test | IEEE 400.2 / IEC 60502-2 | OHMMETER | AUDITOR (H) | H (Hold Point) | SCHEDULED M7
HEL-IR-SUB-001 | QA/QC ITP | WP-CON-SUB-ERE | 220kV 100MVA MPT Impact Recorder Check (<=4.0g), SFRA & Relay Test | IEC 60076-18 / POWERTRANS / PUE | OHMMETER | AUDITOR (H), GRIDMASTER | H (Hold Point) | SCHEDULED M10-M16
PTW-GEN-001 | HSE Permit | WP-CON-MOB | Site Mobilization, Survey Peg-Out & Temporary Facilities Permit | HEL-HS-PLN-0001 / SanPiN 0289-10 | AEGIS / GUARDIAN | INSPECTOR | PTW Active | APPROVED
UZ-PRM-001 | Statutory | WP-CON-MOB | Bukhara Regional Hokimiyat 250 Ha Land Allocation Decree | Land Code of Uzbekistan | PERMIT / SUMMIT | INSPECTOR | Permit Gate | APPROVED
UZ-PRM-002 | Statutory | WP-CON-MOB | State Environmental Expertise (SEE / ZVOS) & EMP Clearance | Goskompriroda / IFC PS1-PS8 | PERMIT / VERDANT | INSPECTOR | Permit Gate | APPROVED
UZ-PRM-003 | Statutory | WP-CON-CIV-PIL | Territorial GASN Construction Permit & KMK State Expertise | Urban Planning Code / KMK 2.02.01-98 | PERMIT / ARCHON | INSPECTOR | Permit Gate | IN REVIEW
UZ-PRM-006 | Statutory | WP-PROC-TRA | GOST-UZ Certificate of Conformity for 220kV MPT & GIS | Uzstandard / Khorgos Customs Code | ROUTE / PERMIT | INSPECTOR | Customs Gate | WATCH
UZ-PRM-007 | Statutory | WP-TNC-ALL | Uzenergoinspeksiya Admission Act for Energisation (Akt Dopuska) | PUE / UzbekEnergo Grid Code | PERMIT / IGNITE | GRIDMASTER, INSPECTOR | Energisation Gate | SCHEDULED M16

## FIDIC_Commercial_Claims
HELIOS EPC — FIDIC YELLOW BOOK COMMERCIAL LEDGER & 17 PRE-PLANTED SIMULATION EVENTS
Custodians: COUNSEL (Contracts Mgr), CLAIMS (Claims Eng), INVOICE (Billing QS), CHECKER (Sub Verifier) ¦ Sub-Clause 20.1: 28-Day Notice Bar
Event ID | Phase / Month | Trigger Sim Days | Pre-Planted Event Description | Primary Agents Hit | FIDIC Sub-Clause | 28d Notice Required? | Expected Technical & Commercial Chain Reaction | Critical Path? | Day 001 Status
EVT-001 | P1 / M01 | Days 004-015 | Geotechnical report shows rock layer at 0.8m in Block 6 (design assumed 1.5m) | TERRA, MERIDIAN, BASTION, KRONOS, COUNSEL | Sub-Clause 4.12 & 20.1 | YES (28d Bar) | TERRA issues FDC-CIV-001 (DTH pre-drill), COUNSEL serves 4.12 notice, KRONOS logs DEL-001 | No (+45d Float) | SEEDED (D004)
EVT-002 | P1 / M02 | Days 030-045 | UzbekEnergo requests protection philosophy resubmission — new grid code PFR | VOLTA, CIPHER, ARCHON, KRONOS, COUNSEL, GRIDMASTER | Sub-Clause 13.7 & 20.1 | YES (28d Bar) | INVERSA PPC firmware update, CIPHER revises HEL-PR-PHL-0200, COUNSEL serves 20.1 notice | YES (0d Float) | SEEDED
EVT-003 | P1 / M03 | Days 065-080 | Module vendor (LUMINOS) requests 8-week delivery extension (cell shortage) | FORGE, CONVOY, KRONOS, WATT, CLAIMS, LUMINOS | PO LD Clause & 8.4 | Vendor LD Notice | WATT flags near-critical erosion, CONVOY negotiates split block-train shipments, KRONOS TIA | Near-Critical | SEEDED
EVT-004 | P2 / M04 | Days 095-108 | Severe Kyzylkum dust storm shuts down outdoor installation for 3 days | AEGIS, GUARDIAN, STRATUM, EREKTOR, KRONOS | Sub-Clause 8.4(c) / 19 | YES (Weather Log) | AEGIS issues site SWO, EREKTOR claims standby, KRONOS logs weather delay vs baseline | No (Float) | SEEDED
EVT-005 | P2 / M05 | Days 120-135 | GROUNDWORK pile driving crew reduced from 4 rigs to 2 (cylinder breakdown) | BASTION, VECTOR, RAMPART, KRONOS, LEDGER, GROUNDWORK | Subcontract Default | Sub Cure Notice | Daily piling drops 50%, RAMPART issues 7-day cure notice, LEDGER quantifies back-charge | No (Local) | SEEDED
EVT-006 | P2 / M06 | Days 145-160 | NCR raised: 47 piles in Block 3 out of tolerance (E-W deviation >20mm) | STRATUM, TORQUE, SENTINEL, EREKTOR, TERRA, PRISM | Sub-Clause 7.5 / 7.6 | Category B NCR | SENTINEL issues NCR, EREKTOR refuses handover, PRISM joint survey, re-drive/slot remedy | No (Local) | SEEDED
EVT-007 | P2 / M07 | Days 175-190 | 33kV MV cable straight joint J-037 fails 0.1Hz VLF test on Circuit INV3 | ARCLINE, OHMMETER, ELECTRA, VOLTA, KRONOS | Sub-Clause 7.4 / ITP | Category B NCR | Testing stopped, TDR fault location, ELECTRA cuts out & re-joints in tent, extended VLF test | No (Local) | SEEDED
EVT-008 | P2 / M08 | Days 200-215 | Client (PATRON) rejects MPR — claims progress is overstated by 8% | SIGMA, KRONOS, ATLAS, COUNSEL, INVOICE, PATRON, AUDITOR | Sub-Clause 14.6 | IPC Dispute | SIGMA reconciles Rule of Credit with AUDITOR, COUNSEL submits formal contractual rebuttal | Commercial | SEEDED
EVT-009 | P3 / M09 | Days 230-245 | 220kV 100MVA MPT held at Khorgos border — missing GOST-UZ certificate | ROUTE, TRACER, CONVOY, KRONOS, COUNSEL, POWERTRANS | Sub-Clause 8.4(e) & 20.1 | YES (28d Bar) | ROUTE mobilizes Tashkent broker, POWERTRANS sends GOST passport, COUNSEL files EOT notice | YES (0d Float) | SEEDED
EVT-010 | P3 / M10 | Days 260-275 | 220kV MPT arrives with 3-axis impact recorder showing 5.2g (threshold 4g) | TRACER, VAULT, SWITCHMAN, RELAY, CONVOY, POWERTRANS | Sub-Clause 18.2 / OEM | Marine Insurance | VAULT quarantines MPT, POWERTRANS runs IEC 60076-18 SFRA test, LEDGE logs cargo claim | YES (0d Float) | SEEDED
EVT-011 | P3 / M11 | Days 285-300 | Subcontractor ELECTRA threatens to demobilise — claims 3 months unpaid IPCs | CHECKER, INVOICE, COUNSEL, RAMPART, ATLAS, ELECTRA | Subcontract Payment | 14d Suspension | CHECKER audits JMC overclaims, COUNSEL reviews pay-when-paid, ATLAS escalates to Danesh | Near-Critical | SEEDED
EVT-012 | P3 / M12 | Days 315-330 | Extreme winter (-26C) — ground frozen solid, piling & concrete halted 18d | AEGIS, VECTOR, BASTION, KRONOS, CLAIMS, INSPECTOR | Sub-Clause 8.4(c) & 20.1 | YES (28d Bar) | KRONOS compares 10-yr Bukhara met data for exceptional climatic entitlement, CLAIMS files EOT | Weather Path | SEEDED
EVT-013 | P4 / M13 | Days 340-355 | PATRON issues scope change instruction — add 5MW BESS reserve area | ATLAS, COUNSEL, KRONOS, ARCHON, LEDGER, PATRON | Sub-Clause 13.1 & 13.3 | YES (VO Proposal) | COUNSEL logs Variation Order, ARCHON designs 33kV feeder bay & civil pad, LEDGER prices VO | Scope Change | SEEDED
EVT-014 | P4 / M14 | Days 370-385 | Protection relay settings rejected by UzbekEnergo — new reactive power spec | CIPHER, VOLTA, RELAY, GRIDLOCK, KRONOS, GRIDMASTER | Sub-Clause 8.4(e) & 20.1 | YES (28d Bar) | CIPHER & INVERSA recalculate Q-curves, RELAY re-programs IEDs and repeats injection tests | YES (0d Float) | SEEDED
EVT-015 | P4 / M15 | Days 395-410 | IV curve test shows 12% of strings in Block 4 below Fill Factor (<72%) | SPARK, OHMMETER, AMPERE, EREKTOR, SENTINEL, LUMINOS | OEM Warranty / 7.5 | RMA Claim | EL imaging finds microcracks in 200 modules; LUMINOS replaces from spare buffer | Near-Critical | SEEDED
EVT-016 | P4 / M16 | Days 425-440 | UzbekEnergo delays energisation consent by 4 weeks — approval backlog | GRIDLOCK, IGNITE, KRONOS, COUNSEL, ATLAS, GRIDMASTER | Sub-Clause 8.4(e) & 20.1 | YES (28d Bar) | COUNSEL serves authority delay EOT notice, KRONOS updates COD forecast, Danesh escalates | YES (0d Float) | SEEDED
EVT-017 | P4 / M17 | Days 455-470 | Performance Ratio (PR) test result: 76.2% (target 80.0%) — below PAC gate | IGNITE, GRIDLOCK, SPARK, SIGMA, PATRON, CERTIFIER | Sub-Clause 9.4 & 10.1 | PAC Withheld | CERTIFIER/PATRON withhold PAC; T&C cleans modules, recalibrates pyranometers & re-tests 7d | YES (COD Gate) | SEEDED

## Coded_Mail_Channels
HELIOS EPC — CODED COMMUNICATION CHANNELS, MAIL NUMBERING STANDARD & DAY 001 LOG
Format: HEL-D{DDD}-{FROM_DEPT}-{TO_DEPT}-{WORK_CODE}-{TYPE}-{NNNN} ¦ Dual Storage: GitHub Issues Channels + Departmental Communications_<DEPT>.md
Channel Code | GitHub Issue # | Channel Title & Scope | Primary Owning Dept | Participating Agents | Allowed Mail Types | Work Codes Covered | Repo Folder Mirror (.md) | Response SLA | Channel Status
CH-01 | Issue #11 | [CH-01 ¦ PD-EXEC] Executive PD Briefings, Directives & Event Injections | PMO / EXT | DANESH (PD), ATLAS, NEXUS | RPT, INS, ESC, EVT | MOB, GEN, ALL | 00_Project_Overview/Communications_PMO.md | Same Sim Day | ACTIVE
CH-02 | Issue #12 | [CH-02 ¦ PMO-PLN] Master Schedule, EVM Controls, DPR/WPR/MPR & Action Chasers | PLN / PMO | ATLAS, NEXUS, KRONOS, VECTOR, WATT, SIGMA, LEDGER | RPT, DEL, INS, MOM | MOB, GEN, ALL | 01_Planning_Controls/Communications_PLN.md | Same Sim Day | ACTIVE
CH-03 | Issue #13 | [CH-03 ¦ ENG-DES] Engineering Design, Submittals, RFIs, FDCs & Technical Queries | ENG | ARCHON, TERRA, MERIDIAN, SOLARIS, AMPERE, VOLTA, CIPHER, NEXGEN, HERALD | RFI, INS, RPT, ESC | CIV, PIL, TRK, MOD, SUB | 02_Engineering_Design/Communications_ENG.md | Max 2 Sim Days | ACTIVE
CH-04 | Issue #14 | [CH-04 ¦ SCM-LOG] Procurement, TBE/CBE, Factory Expediting, Khorgos Customs & Stores | SCM / EXT | CONVOY, FORGE, DEPOT, VENDOR, TRACER, ROUTE, VAULT, LUMINOS, INVERSA, POWERTRANS | INS, RPT, NTC, ESC | PIL, TRK, MOD, INV, TRA, GIS | 03_SCM/Communications_SCM.md | Max 2 Sim Days | ACTIVE
CH-05 | Issue #15 | [CH-05 ¦ CON-CIV] PV Field Civil, Earthworks, Piling & Tracker Erection Workfront | CON / SUB | RAMPART, BASTION, STRATUM, PRISM, GROUNDWORK, EREKTOR | INS, RFI, RPT, ESC | MOB, CIV, PIL, TRK, MOD | 04_Construction/Communications_CON.md | Same Sim Day | ACTIVE
CH-06 | Issue #16 | [CH-06 ¦ CON-ELE] DC/MV Cabling, PCS Skids & 33/220kV Substation Civil/E&M Workfront | CON / SUB | RAMPART, CONDUIT, ARCLINE, FORTRESS, SWITCHMAN, ELECTRA, GRIDCON | INS, RFI, RPT, ESC | CAB, INV, FND, SUB | 04_Construction/Communications_CON.md | Same Sim Day | ACTIVE
CH-07 | Issue #17 | [CH-07 ¦ QAQ-ITP] Quality Assurance, ITP Hold Points, Load Tests & NCR Management | QAQ / EXT | SENTINEL, PLUMBLINE, TORQUE, OHMMETER, DOSSIER, AUDITOR, CERTIFIER | NCR, INS, RPT, ESC | CIV, PIL, TRK, MOD, CAB, SUB | 05_Quality/Communications_QAQ.md | Same Sim Day | ACTIVE
CH-08 | Issue #18 | [CH-08 ¦ EHS-PRM] HSE Safety, PTW Permits, Environmental & Uzbekistan Statutory Liaison | EHS / ADM | AEGIS, GUARDIAN, WARDEN, VERDANT, SUMMIT, PERMIT, INSPECTOR | INS, NCR, RPT, ESC | MOB, CIV, PIL, SUB, GEN | 06_EHS/Communications_EHS.md | Immediate (SWA) | ACTIVE
CH-09 | Issue #19 | [CH-09 ¦ COM-FID] FIDIC Contracts, Sub-Clause 20.1 Notices, Claims, VOs & IPC/JMC Billing | COM / EXT | COUNSEL, CLAIMS, INVOICE, CHECKER, LEDGE, LEDGER2, PATRON | NTC, VO, BIL, DEL, ESC | ALL WORK CODES | 07_Contracts/Communications_COM.md | Same Sim Day | ACTIVE
CH-10 | Issue #20 | [CH-10 ¦ TNC-GRD] Testing, Commissioning, Relay Settings, UzbekEnergo Grid Sync & PAC | TNC / EXT | IGNITE, SPARK, RELAY, GRIDLOCK, GRIDMASTER, CERTIFIER, PATRON | INS, RPT, NTC, ESC | TNC, SUB, MOD, INV | 08_TC/Communications_TNC.md | Same Sim Day | ACTIVE
Mail Code (Msg-ID) | Sim Day & Time | Channel | From Agent (Dept) | To Agent (Dept) | Work Code | Mail Type | Priority | Subject / Topic | Status
HEL-D001-PMO-PMO-MOB-INS-0001 | Day 001 08:00 | CH-02 (#12) | ATLAS (PMO) | ALL (PMO) | MOB | INS | HIGH | LNTP Project Kickoff Directive: Mobilization, MDR Submittals & Long-Lead RFQ Release | CLOSED
HEL-D001-PLN-PMO-MOB-RPT-0002 | Day 001 17:00 | CH-02 (#12) | SIGMA (PLN) | KRONOS (PLN) | MOB | RPT | HIGH | DPR Day 001 Compilation & Rev 0 Baseline S-Curve Verification (SPI 0.9965 / CPI 0.9462) | CLOSED
HEL-D001-PMO-EXT-MOB-RPT-0003 | Day 001 18:00 | CH-01 (#11) | ATLAS (PMO) | DANESH (EXT) | MOB | RPT | HIGH | [PD BRIEF] Day 001 Executive Brief: LNTP Kickoff Complete, 64 Agents Active, Zero Blockers | CLOSED