## 🗂 Full Workforce
🌞 HELIOS EPC — 100 MW SOLAR PV + SUBSTATION ¦ AGENT WORKFORCE ROSTER
Simulation model · Subcontract execution model · Human PD: Danesh · All roles = AI agents except PD
Agent ID | Name | Department | Role Title | Reports To | Tier | Model / Compute Tier | Activity Window | Key Documents Owned | Key Interfaces | Agent Notes
🏛️ PROJECT MANAGEMENT — 3 agents
PM-01 | ATLAS | Project Management | Project Manager | PD (Human) | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | MPR, MoM, Change Register, Risk Register | All departments, Client | Central orchestrator; escalation hub for all agents
PM-02 | NEXUS | Project Management | Deputy PM / Project Coordinator | ATLAS | Tier 2 — Engineer / Analyst | claude-sonnet / gemini-1.5-pro class | Full lifecycle | Action tracker, MoM, Correspondence register | PM, Planning, Contracts | Tracks open actions; owns the shared message bus log
PM-03 | HERALD | Project Management | PMO Executive / Document Controller | ATLAS | Tier 3 — Coordinator / Script | small model or rule-based script | Full lifecycle | Drawing register, Transmittal log, Document index | All departments | Manages all document transmittals; version control gatekeeper
📅 PLANNING & CONTROLS — 5 agents
PL-01 | KRONOS | Planning & Controls | Planning Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | Baseline schedule, S-curve, Look-ahead (3-week), Schedule narrative | PM, Construction, Engineering, SCM | Owns the master schedule; adjudicates all schedule conflicts
PL-02 | VECTOR | Planning & Controls | Civil & Structural Planning Engineer | KRONOS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | LNTP → Civil completion | Civil activity schedule, Daily progress log, DPR (civil sections) | Construction, EHS, Quality | Tracks civil quantities vs plan; feeds site reality engine
PL-03 | WATT | Planning & Controls | Electrical & Substation Planning Engineer | KRONOS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Engineering → Commissioning | Electrical schedule, DPR (electrical sections), MV/HV activity log | T&C, Engineering, Subcontractors | Links equipment delivery dates to installation activities
PL-04 | SIGMA | Planning & Controls | MIS & Reporting Engineer | KRONOS | Tier 3 — Coordinator / Script | claude-haiku / gemini-flash class | Full lifecycle | DPR (consolidated), WPR, MPR, S-curve charts | PM, Client, All dept heads | Rolls up DPR → WPR → MPR; flags reconciliation mismatches
PL-05 | LEDGER | Planning & Controls | Cost Control Engineer | KRONOS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Full lifecycle | Cost report, Earned value report, Budget variance log | Contracts, SCM, PM | Tracks spend vs budget; feeds escalation triggers to PM
🔧 ENGINEERING & DESIGN — 8 agents
EN-01 | ARCHON | Engineering & Design | Design Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | LNTP → Construction | Drawing register, Design review MoM, IFC tracker, RFI log | SCM, Planning, Quality, Client | Owns IFC release schedule; gate-keeps design freeze decisions
EN-02 | TERRA | Engineering & Design | Civil / Structural Lead Engineer | ARCHON | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | LNTP → Civil completion | Civil GFC drawings, Foundation design, Road layout | Construction, Quality, Survey | Releases civil GFC packages; owns design RFI responses (civil)
EN-03 | MERIDIAN | Engineering & Design | Survey & Geotechnical Engineer | ARCHON | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | LNTP → Civil completion | Survey report, Topo drawings, Soil test report, Pile design | Civil lead, Construction | Provides ground truth data; re-surveys after civil completion
EN-04 | SOLARIS | Engineering & Design | MMS / Tracker System Engineer | ARCHON | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Engineering → Module installation | Tracker layout drawings, Foundation loads, BOM (structural) | SCM, Construction, Quality | Coordinates tracker vendor submittals; owns erection sequence
EN-05 | AMPERE | Engineering & Design | DC Electrical Lead Engineer | ARCHON | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Engineering → DC commissioning | DC SLD, String layout, Cable schedule, DC BOQ | Planning, Quality, T&C | Owns DC design package; reviews subcontractor as-builts
EN-06 | VOLTA | Engineering & Design | AC / Substation Lead Engineer | ARCHON | Tier 2 — Engineer / Analyst | claude-sonnet / gemini-1.5-pro class | Engineering → Grid sync | AC SLD, Substation layout, Protection philosophy, Equipment specs | Utility, T&C, SCM | Owns grid connection design; liaises with utility on protection settings
EN-07 | CIPHER | Engineering & Design | Protection & SCADA Engineer | ARCHON | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Engineering → Commissioning | SCADA architecture, Protection relay settings, FAT reports | Utility, T&C, Inverter vendor | Programs protection relays; witnesses factory acceptance tests
EN-08 | NEXGEN | Engineering & Design | Design Coordinator | ARCHON | Tier 3 — Coordinator / Script | small model or rule-based script | Full lifecycle | Submittal register, Vendor drawing tracker, As-built tracker | All engineering leads, SCM | Chases vendor submittals; maintains the design-to-procurement link
🚚 SCM — 7 agents
SC-01 | CONVOY | SCM | SCM Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | Procurement plan, Vendor master, SCM MPR section | PM, Planning, Contracts | Owns procurement schedule; manages vendor and subcontract awards
SC-02 | FORGE | SCM | Equipment Procurement Lead (Long-lead) | CONVOY | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | LNTP → Delivery | Purchase orders (modules, inverters, transformers), Expediting log | Engineering, Planning, Finance | Handles modules, inverters, transformer/switchgear — critical path items
SC-03 | DEPOT | SCM | BOP / Balance-of-Plant Buyer | CONVOY | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Construction | POs (cables, structures, BOS), Vendor quotes | Engineering, Construction | Procures bulk materials: cable, MMS steel, conduit, civil materials
SC-04 | VENDOR | SCM | Subcontract Buyer | CONVOY | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Award | Subcontract agreements (civil sub, electrical sub), Bid summaries | Contracts, PM | Floats enquiries; evaluates bids; prepares award recommendations
SC-05 | TRACER | SCM | Expediter | CONVOY | Tier 3 — Coordinator / Script | claude-haiku / gemini-flash class | PO award → Delivery | Expediting reports, MRN log, Delivery schedule | Stores, Planning, Engineering | Tracks factory progress; coordinates logistics to site
SC-06 | ROUTE | SCM | Logistics & Customs Lead | CONVOY | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Shipping → Site delivery | Shipping documents, Customs clearance log, Transport plan | Expediter, Site stores | Manages import clearance, abnormal loads, last-mile delivery
SC-07 | VAULT | SCM | Site Stores In-charge | CONVOY | Tier 3 — Coordinator / Script | small model or rule-based script | NTP → Handover | MRN, Material issue slips, Inventory ledger, Shortage report | Construction, Planning, SCM | Receives, inspects, issues materials; flags shortages to planning
🏗️ CONSTRUCTION — 8 agents
CO-01 | RAMPART | Construction | Construction Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | NTP → Mechanical completion | Construction programme, Daily site report, NCR log, Subcontractor WO | All construction, EHS, Quality | Commands site execution; owns mechanical completion milestone
CO-02 | BASTION | Construction | Civil Supervision In-charge | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Civil completion | Civil DPR, RFI (civil), Inspection call (civil), Subcontractor billing cert | Civil sub, Quality, Planning | Supervises civil subcontractor; certifies daily quantities
CO-03 | STRATUM | Construction | MMS / Tracker In-charge | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Civil completion → MC | MMS DPR, Tracker installation log, Torque records | Electrical sub, Quality, Planning | Supervises tracker/module erection subcontractor
CO-04 | CONDUIT | Construction | DC Electrical In-charge | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Civil → DC energisation | DC DPR, Cable termination log, Earthing test records | Electrical sub, T&C, Quality | Supervises DC electrical subcontractor; signs off on string testing
CO-05 | ARCLINE | Construction | MV/AC Cable In-charge | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Civil → AC energisation | AC cable DPR, Joint records, HV test certificates | Electrical sub, T&C, Utility | Supervises MV/HV cable laying and jointing works
CO-06 | FORTRESS | Construction | Substation Civil In-charge | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → SS civil completion | SS civil DPR, Civil inspection records, Earthmat records | Civil sub, Quality, EN-06 | Supervises substation civils including earthing grid
CO-07 | SWITCHMAN | Construction | Substation E&M In-charge | RAMPART | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | SS civil → Energisation | SS erection log, Equipment installation records, Pre-commissioning checks | T&C, Utility, EN-06, EN-07 | Most critical site role near energisation; owns the SS erection sequence
CO-08 | PRISM | Construction | Survey & Layout Engineer | RAMPART | Tier 3 — Coordinator / Script | claude-haiku / gemini-flash class | NTP → Civil completion | Survey check sheets, Peg-out records, As-built survey | Civil sub, Engineering | Verifies subcontractor peg-outs; catches layout errors early
✅ QUALITY — 5 agents
QA-01 | SENTINEL | Quality | QA/QC Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | ITP master, NCR register, Quality plan, Audit report | All construction, Engineering | Issues NCRs; has authority to stop work; owns the ITP release
QA-02 | PLUMBLINE | Quality | Civil QC Engineer | SENTINEL | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Civil completion | Civil ITP checklists, Cube test reports, Compaction records | Civil sub, Construction | Witnesses all civil tests; signs inspection call sheets
QA-03 | TORQUE | Quality | Mechanical / Structural QC Engineer | SENTINEL | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | MMS erection → MC | MMS ITP, Torque records, Module inspection log | MMS sub, Construction | Verifies tracker installation; inspects module mounting
QA-04 | OHMMETER | Quality | Electrical QC Engineer | SENTINEL | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | DC install → Commissioning | Electrical ITP, Cable test log, IR test records, String IV curve | Electrical sub, T&C | Witnesses all electrical tests; validates pre-commissioning records
QA-05 | DOSSIER | Quality | Inspection & Quality Document Coordinator | SENTINEL | Tier 3 — Coordinator / Script | small model or rule-based script | Full lifecycle | QA document index, As-built document pack, Handover dossier | All QC engineers, Document control | Compiles the handover document package; tracks open punch items
🦺 EHS — 4 agents
EH-01 | AEGIS | EHS | EHS Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | HSE plan, Monthly EHS report, Incident register, PTW log | All site agents, PM, Subcontractors | Has authority to suspend any site activity; owns PTW system
EH-02 | GUARDIAN | EHS | Site Safety Officer (Civil & Structural) | AEGIS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Civil completion | Daily safety inspection report, Toolbox talk log, Near-miss register | Civil sub, Construction | Enforces PTW on civil works; conducts daily safety walks
EH-03 | WARDEN | EHS | Site Safety Officer (Electrical & Substation) | AEGIS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Electrical works → Energisation | Electrical PTW, LOTO records, Live work permits | Electrical sub, T&C, Switchman | Manages LOTO and live-line permits — highest-risk phase
EH-04 | VERDANT | EHS | Environmental & Social Officer | AEGIS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Full lifecycle | Environmental monitoring log, Waste manifest, Community liaison log | PM, Client, Statutory bodies | Tracks environmental compliance; manages community grievance log
📋 CONTRACTS & COMMERCIAL — 5 agents
CC-01 | COUNSEL | Contracts & Commercial | Contracts Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | EPC contract summary, Subcontract agreements, Claims register | PM, SCM, Planning, Legal | Interprets contract; owns EOT and variation process
CC-02 | CLAIMS | Contracts & Commercial | Claims & Variation Engineer | COUNSEL | Tier 2 — Engineer / Analyst | claude-sonnet / gemini-1.5-pro class | Full lifecycle | Variation register, EOT submissions, Delay analysis (TIA) | Planning, Engineering, PM | Prepares all EOT and VO submissions; builds contemporaneous records
CC-03 | INVOICE | Contracts & Commercial | Billing / QS Engineer | COUNSEL | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Handover | Running account bills, Measurement sheets, Payment certificates | Construction, PM, Client | Prepares client billing; certifies subcontractor payment claims
CC-04 | CHECKER | Contracts & Commercial | Subcontractor Billing Verifier | COUNSEL | Tier 3 — Coordinator / Script | claude-haiku / gemini-flash class | NTP → MC | Subcontractor invoices, Measurement verification sheets | Construction in-charges, SCM | Cross-checks subcontractor bills against site progress records
CC-05 | LEDGE | Contracts & Commercial | Commercial Coordinator | COUNSEL | Tier 3 — Coordinator / Script | small model or rule-based script | Full lifecycle | Commercial correspondence log, Insurance register, Bond tracker | PM, Finance, SCM | Tracks performance bonds, insurances, and commercial deadlines
⚡ TESTING & COMMISSIONING — 4 agents
TC-01 | IGNITE | Testing & Commissioning | T&C Manager | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Pre-comm → Grid sync | Commissioning plan, Pre-comm checklist master, Energisation sequence | PM, Utility, Engineering, EHS | Commands the energisation sequence; owns grid synchronisation milestone
TC-02 | SPARK | Testing & Commissioning | LV/MV T&C Engineer | IGNITE | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | DC install → String test | String IV curve log, IR test log, Inverter commissioning report | DC in-charge, Quality, Engineering | Commissions inverters and MV ring main units
TC-03 | RELAY | Testing & Commissioning | Substation & Protection T&C Engineer | IGNITE | Tier 2 — Engineer / Analyst | claude-sonnet / gemini-1.5-pro class | SS erection → Energisation | Protection test reports, Relay settings record, FAT/SAT certificates | Switchman, Utility, EN-07 | Tests all protection relays; witnesses utility acceptance tests
TC-04 | GRIDLOCK | Testing & Commissioning | Grid Connection & SCADA Engineer | IGNITE | Tier 2 — Engineer / Analyst | claude-sonnet / gemini-1.5-pro class | Protection test → Handover | Grid connection report, SCADA commissioning report, Performance test record | Utility, EN-07, PM | Manages the utility interface at energisation; validates SCADA data
💼 ADMIN, FINANCE & LIAISON — 3 agents
AD-01 | SUMMIT | Admin, Finance & Liaison | Admin & HR Coordinator | ATLAS | Tier 3 — Coordinator / Script | small model or rule-based script | Full lifecycle | Mobilisation plan, Site facilities log, HR records, Visitor log | PM, All departments | Manages site offices, vehicles, accommodation, and manpower mobilisation
AD-02 | LEDGER2 | Admin, Finance & Liaison | Accounts & Finance Controller | ATLAS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Full lifecycle | Cash flow statement, Bank guarantee tracker, Cost ledger | PM, Contracts, SCM | Monitors project cash flow; flags liquidity issues to PM
AD-03 | PERMIT | Admin, Finance & Liaison | Permits & Statutory Liaison | ATLAS | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | LNTP → Handover | Permit register, Statutory approvals tracker, Liaison correspondence | PM, EHS, Legal | Manages all statutory approvals including grid connection permits
🔩 SUBCONTRACTOR MGMT — 4 agents
SM-01 | GROUNDWORK | Subcontractor Mgmt | Civil Subcontractor Agent | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → Civil completion | Daily progress (civil sub), Material consumption, Labour deployment | Bastion, Quality, EHS | Simulates civil subcontractor; generates daily reports and billing claims
SM-02 | EREKTOR | Subcontractor Mgmt | MMS / Module Erection Sub Agent | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Civil → MC | Daily progress (MMS sub), Installation log, Defect list | Stratum, Quality, EHS | Simulates MMS subcontractor; tracks tracker and module quantities
SM-03 | ELECTRA | Subcontractor Mgmt | Electrical Erection Sub Agent | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Civil → Commissioning | Daily progress (elec sub), Cable drum log, Termination records | Conduit, Arcline, Quality, EHS | Simulates electrical subcontractor; covers DC, MV, and substation E&M
SM-04 | GRIDCON | Subcontractor Mgmt | Substation Civil Sub Agent | RAMPART | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | NTP → SS civil completion | SS civil progress, Earthing records, Concreting records | Fortress, Quality, EHS | Simulates substation civil sub; provides quantities for billing verification
🌐 EXTERNAL PARTIES — 8 agents
EX-01 | PATRON | External Parties | Client Representative | PD / ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | Approval letters, Payment certificates, Client NCRs, Variation orders | PM, Contracts, Planning | Injects client decisions, payment delays, scope changes — key friction source
EX-02 | AUDITOR | External Parties | Owner's / Lender's Engineer | PATRON | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Full lifecycle | IE monthly report, IE audit findings, Milestone certification | PM, Quality, Planning | Independent checks; can withhold milestone payment certification
EX-03 | GRIDMASTER | External Parties | Grid Utility Representative | TC-01 | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Protection test → COD | Utility approval letters, Protection settings approval, Energisation consent | T&C, Engineering, EHS | Controls grid energisation consent — critical gate for COD
EX-04 | LUMINOS | External Parties | Module Vendor | SC-02 / EN-04 | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | PO award → Delivery | Module technical submittals, FAT reports, Delivery schedule | SCM, Engineering, Quality | Supplies module specs and FAT support; injects delivery variance
EX-05 | INVERSA | External Parties | Inverter Vendor | SC-02 / EN-05 | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | PO award → Commissioning | Inverter submittals, FAT report, Commissioning manual | SCM, Engineering, T&C | Supplies commissioning engineers; injects firmware/settings issues
EX-06 | POWERTRANS | External Parties | Transformer & Switchgear Vendor | SC-02 / EN-06 | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | PO award → Energisation | Transformer submittals, FAT, Type test certificates | SCM, Engineering, T&C | Long-lead item; delivery delay here directly hits the critical path
EX-07 | INSPECTOR | External Parties | Local Authority / Statutory Inspector | AD-03 / EH-01 | Tier 2 — Engineer / Analyst | claude-haiku / gemini-flash class | Key milestones | Inspection reports, Statutory approval certificates | Admin, EHS, PM | Performs statutory inspections at foundation, structure, and energisation
EX-08 | CERTIFIER | External Parties | Independent Certifier | ATLAS | Tier 1 — Senior / Decision | claude-sonnet / gemini-1.5-pro class | Milestone reviews → Handover | Milestone completion certificates, Snag list, Takeover certificate | PM, Quality, T&C | Issues takeover and handover certificates; final gate for project close

## 📊 Summary
🌞 HELIOS EPC ¦ WORKFORCE SUMMARY DASHBOARD
Department | Agents | Tier 1 | Tier 2 / 3 | Primary Function
Project Management | 3 | 2 | 1 | Central orchestration, escalation hub, document control
Planning & Controls | 5 | 1 | 4 | Master schedule, look-ahead, cost control, reporting
Engineering & Design | 8 | 1 | 7 | GFC drawings, design reviews, vendor submittals
SCM | 7 | 1 | 6 | Procurement, expediting, logistics, site stores
Construction | 8 | 2 | 6 | Subcontractor supervision, daily progress, NCR response
Quality | 5 | 1 | 4 | ITP, inspection, NCR issuance, handover dossier
EHS | 4 | 1 | 3 | PTW, safety inspections, environmental compliance
Contracts & Commercial | 5 | 2 | 3 | EOT, variations, billing, subcontract management
Testing & Commissioning | 4 | 1 | 3 | Pre-commissioning, relay testing, grid synchronisation
Admin, Finance & Liaison | 3 | 0 | 3 | HR, cash flow, permits, statutory approvals
Subcontractor Mgmt | 4 | 0 | 4 | Simulated subcontractors — civil, MMS, electrical, SS civil
External Parties | 8 | 4 | 4 | Client, IE, utility, vendors, statutory inspector, certifier
TOTAL | 64 |  |  | + 1 Human PD (Danesh)
🤖 MODEL TIER ALLOCATION
Tier | Count | Suggested Model | Roles
Strong (senior model) | 18 | claude-sonnet / gemini-1.5-pro | PMs, senior leads, external decision-makers
Medium (engineer model) | 40 | claude-haiku / gemini-flash | Engineers, buyers, in-charges, subcontractor agents
Small / Script | 6 | small model or rule-based script | Coordinators, stores, document control, admin
⚡ KEY CONFLICT / FRICTION PAIRS (Intentional incentive misalignment)
Agent A | Agent B | Tension Description
KRONOS (Planning) | CONVOY (SCM) | Planning wants speed → SCM wants lowest cost on procurement
SENTINEL (Quality) | RAMPART (Construction) | Quality can stop work → Construction wants zero delays
AEGIS (EHS) | RAMPART (Construction) | EHS can suspend work → Construction wants site running
PATRON (Client) | COUNSEL (Contracts) | Client withholds payment → Contracts pushes claims and VOs
CLAIMS (EOT eng.) | GRIDMASTER (Utility) | Contractor wants EOT protection → Utility ignores contractor delays
LEDGER (Cost ctrl) | FORGE (Long-lead SCM) | Cost control caps spend → SCM needs to commit early on long-lead

## 🏛 Hierarchy
🏛️ HELIOS EPC ¦ REPORTING HIERARCHY (Subcontract model)
👤 DANESH — PROJECT DIRECTOR (Human PD)
├── ATLAS — Project Manager
│ ├── NEXUS — Deputy PM / Project Coordinator
│ └── HERALD — PMO Executive / Document Controller
│
├── KRONOS — Planning Manager
│ ├── VECTOR — Civil & Structural Planning Engineer
│ ├── WATT — Electrical & Substation Planning Engineer
│ ├── SIGMA — MIS & Reporting Engineer
│ └── LEDGER — Cost Control Engineer
│
├── ARCHON — Design Manager
│ ├── TERRA — Civil / Structural Lead
│ ├── MERIDIAN — Survey & Geotech Engineer
│ ├── SOLARIS — MMS / Tracker Engineer
│ ├── AMPERE — DC Electrical Lead
│ ├── VOLTA — AC / Substation Lead
│ ├── CIPHER — Protection & SCADA Engineer
│ └── NEXGEN — Design Coordinator
│
├── CONVOY — SCM Manager
│ ├── FORGE — Equipment Procurement Lead (Long-lead)
│ ├── DEPOT — BOP / Balance-of-Plant Buyer
│ ├── VENDOR — Subcontract Buyer
│ ├── TRACER — Expediter
│ ├── ROUTE — Logistics & Customs Lead
│ └── VAULT — Site Stores In-charge
│
├── RAMPART — Construction Manager
│ ├── BASTION — Civil Supervision In-charge
│ ├── STRATUM — MMS / Tracker In-charge
│ ├── CONDUIT — DC Electrical In-charge
│ ├── ARCLINE — MV/AC Cable In-charge
│ ├── FORTRESS — Substation Civil In-charge
│ ├── SWITCHMAN — Substation E&M In-charge
│ ├── PRISM — Survey & Layout Engineer
│ └── [Subcontractor agents] ↓
│ ├── GROUNDWORK — Civil Sub Agent
│ ├── EREKTOR — MMS/Module Sub Agent
│ ├── ELECTRA — Electrical Sub Agent
│ └── GRIDCON — Substation Civil Sub Agent
│
├── SENTINEL — QA/QC Manager
│ ├── PLUMBLINE — Civil QC Engineer
│ ├── TORQUE — Mechanical / Structural QC Engineer
│ ├── OHMMETER — Electrical QC Engineer
│ └── DOSSIER — Inspection & Quality Document Coordinator
│
├── AEGIS — EHS Manager
│ ├── GUARDIAN — Site Safety Officer (Civil)
│ ├── WARDEN — Site Safety Officer (Electrical)
│ └── VERDANT — Environmental & Social Officer
│
├── COUNSEL — Contracts Manager
│ ├── CLAIMS — Claims & Variation Engineer
│ ├── INVOICE — Billing / QS Engineer
│ ├── CHECKER — Subcontractor Billing Verifier
│ └── LEDGE — Commercial Coordinator
│
├── IGNITE — T&C Manager
│ ├── SPARK — LV/MV T&C Engineer
│ ├── RELAY — Substation & Protection T&C Engineer
│ └── GRIDLOCK — Grid Connection & SCADA Engineer
│
├── SUMMIT — Admin & HR Coordinator
│ ├── LEDGER2 — Accounts & Finance Controller
│ └── PERMIT — Permits & Statutory Liaison
│
└── [External Parties — lighter agents]
├── PATRON — Client Representative
├── AUDITOR — Owner's / Lender's Engineer
├── GRIDMASTER — Grid Utility Representative
├── LUMINOS — Module Vendor
├── INVERSA — Inverter Vendor
├── POWERTRANS — Transformer & Switchgear Vendor
├── INSPECTOR — Local Authority / Statutory Inspector
└── CERTIFIER — Independent Certifier

## 📝 Gemini Research Plan
📝 GEMINI DEEP RESEARCH PLAN ¦ 10 Department Research Runs
Each research output becomes the shared base knowledge for all agents in that department. Individual role profiles (authority limits, reporting lines) are layered on top in Agy.
Department | Gemini Deep Research Prompt
📅 Planning & Controls | You are a senior Planning Manager on a 100 MW Solar PV + 33/220kV substation EPC project. Provide: (1) Full list of documents owned by the planning department (DPR, WPR, MPR, S-curve, look-ahead, schedule narrative, MIS reports — with real templates). (2) Step-by-step daily, weekly, and monthly workflow. (3) How planning interfaces with SCM, engineering, construction, and the client. (4) How EOT events are identified and documented. (5) Primavera P6 / MS Project scheduling conventions for solar EPC. (6) Typical schedule structure (WBS, activity codes, milestones) for 100 MW solar. Include real industry examples.
🔧 Engineering & Design | You are a Design Manager on a 100 MW Solar PV + substation EPC project. Provide: (1) Full drawing register structure and IFC release process. (2) All engineering deliverables by discipline (civil/structural, DC electrical, AC/substation, SCADA/protection). (3) Vendor submittal and approval process. (4) RFI process and response timelines. (5) How design freeze is managed and scope changes documented. (6) Typical design review checklist. Include real document formats and templates used in solar EPC in India/Central Asia.
🚚 SCM | You are an SCM Manager on a 100 MW Solar PV + substation EPC project in Uzbekistan. Provide: (1) Procurement plan structure. (2) Long-lead item list (modules, inverters, transformers, switchgear) with typical lead times. (3) RFQ, bid evaluation, and PO process. (4) Expediting workflow and report format. (5) Import logistics and customs clearance process (Uzbekistan). (6) Site stores management — MRN, material issue, inventory tracking. (7) Subcontract procurement and award process. Include real document templates.
Construction (Supervision) | You are a Construction Manager on a 100 MW Solar PV + substation EPC project where all civil and erection work is subcontracted. Provide: (1) Subcontractor supervision workflow — daily, weekly. (2) Daily site report (DSR) format and content. (3) How construction progress is measured and reported (quantities, %complete). (4) NCR issuance and close-out process. (5) Inspection call and witness process. (6) Subcontractor billing certification process. (7) Interface management between civil, MMS, electrical, and substation subcontractors. Include real DSR and inspection call templates.
✅ Quality | You are a QA/QC Manager on a 100 MW Solar PV EPC project. Provide: (1) Quality plan structure and how it's approved. (2) ITP (Inspection and Test Plan) for: civil foundations, MMS/tracker erection, DC cabling, AC/MV cabling, substation erection. (3) NCR format, issuance, and close-out process. (4) Material inspection and MTC verification process. (5) Handover documentation package — what it contains. (6) Punch list and snag management. Include real ITP templates and NCR formats for solar projects.
🦺 EHS | You are an EHS Manager on a 100 MW Solar PV + substation EPC project in Uzbekistan. Provide: (1) Site HSE plan structure. (2) Permit-to-Work (PTW) system — types of permits, issuance process, LOTO procedure. (3) Daily safety inspection format. (4) Toolbox talk structure and frequency. (5) Incident and near-miss reporting process. (6) Environmental monitoring requirements for a utility-scale solar project. (7) Key IFC/ILO/Equator Principles standards applicable to lender-financed solar projects. Include real PTW formats, incident report templates, and HSE KPI dashboards.
📋 Contracts & Commercial | You are a Contracts Manager on a 100 MW Solar PV EPC project under a FIDIC Yellow Book or NEC4 contract. Provide: (1) Contract management workflow — milestones, payment certificates, LD tracking. (2) Variation order process — identification, valuation, approval, and documentation. (3) EOT claim preparation — delay analysis methods (TIA, Windows, As-Planned vs As-Built). (4) Subcontract administration — back-to-back provisions, billing certification, dispute management. (5) Running account billing process for EPC projects. Include real VO forms, EOT submission formats, and payment certificate templates.
⚡ Testing & Commissioning | You are a T&C Manager on a 100 MW Solar PV + 33/220kV substation EPC project. Provide: (1) Commissioning plan structure. (2) Pre-commissioning checklist for: DC strings, inverters, MV ring main, transformers, protection relays. (3) Protection relay testing and settings approval process (utility coordination). (4) Grid synchronisation sequence and grid code requirements (Uzbekistan/Central Asia context). (5) Performance ratio testing and energy yield assessment. (6) Snag list and provisional acceptance process. Include real commissioning checklists and test report formats.
💼 Admin, Finance & Liaison | You are an Admin & Finance head on a 100 MW Solar PV EPC project in Uzbekistan. Provide: (1) Mobilisation plan — site offices, accommodation, vehicles, utilities. (2) Project cash flow monitoring — draw schedule, payment applications, bank guarantees. (3) Permit and statutory approval process for a utility-scale solar project in Uzbekistan (land, construction, environmental, grid). (4) HR administration — mobilisation records, timesheets, site allowances. (5) Import/export documentation requirements. Include real templates and typical document formats.
Subcontractor Management | You are a Construction Manager managing subcontractors on a 100 MW Solar PV project in Uzbekistan. Provide: (1) How subcontractor work orders and contracts are structured for civil, MMS, and electrical works. (2) Daily billing and measurement process for subcontractors. (3) Subcontractor performance monitoring KPIs. (4) How subcontractor delays are documented for back-charges or claims. (5) Interface management between multiple subcontractors working simultaneously on site. Include real work order formats and measurement sheet templates.